## Slide 1
NOAA Proving Ground / User Readiness Meeting
AWIPS Readiness
Steve Schotz and Ed Mandel
May 10, 2016

## Slide 2: Agenda
AWIPS Release Summary
NCEP NAWIPS Migration Summary
AWIPS Satellite Plug-In Summary
GOES-R Product Readiness Summary
2016 GOES-R Simulated Product Data Activation Dates
AWIPS II Data Delivery Status

## Slide 3: AWIPS Release Summary
Completed deployment of AWIPS II to WFOs, NCs, RFC Centers and Regional HQ Systems – FY 2015
Deploying AWIPS Releases (15 releases 14.3.1 to 16.3.1)
  New functionality: 379 DCSs, CFRs 54, and 1346 DRs including:
    Data Delivery, Collaboration, HRRR, MRMS, National Blend, BMH, Tropical, Lightning, FDSE, Damage Path Tool, Mixed case, Data Access Framework, Meteogram, Impact Catalog, SAILS, Improved Install times
    DR surge effort of 170 Priority 2 DRs completed (as of 5/7/16)
  Gathering FY17 development tasks from NWS AOP process , NWS Governance process, and SREC process
  Improving process to include SMEs, testers and training as part of the development cycle
  Implementing a local applications review process for science, code, and security
AWIPS II Release Summary and Schedule (Deployment Start)
  16.1.1  Major Functionality – December 2015
  16.1.2 Tropical 2016/Severe Weather, MPE – April 2016
  16.1.3  Broadcast Message Handling (CRS replacement) – April 2016
  16.1.4  National Centers Specific – April 2016
  16.2.1  Major Functionality – May 2016 (Satellite Plug-ins included)
  16.2.2  Major Functionality – July 2016
  16.3.1  COTS (JAVA/Eclipse) – August 2016
  16.4.1  Major Functionality – November 2016 (Satellite Plug-ins included)

## Slide 4: National Centers AWIPS (NAWIPS) Migration Status
Relooking at approach/schedule based on OPC test and evaluations
  Preparing Test Scenarios for all the centers (including potential system performance areas
  Schedule re-baselining in progress
    Current order of sites is OPC, CPC, NCO, NHC, WPC, SPC, AWC, and SWPC
NAWIPS will be used at most Centers to ingest and display GOES-R products in CY 2017
  ISatSS will generate necessary McIdas Files for NAWIPS consumption

## Slide 5: AWIPS Satellite Plugin Summary
Develop/Deploy configurable Sat Ingest/Display “plug-ins” for AWIPS2
  GOES-R and Himawari:
    Sectorized Cloud and Moisture Imagery, Derived Products for GOES-R, Advanced Himawari Imager (AHI) (Baselined in 15.x)
  Pointset and netcdfGrid:
    Display of any raster given Lat, Lon, Value. Use for new Polar Products (A2 16.2.1)
  Enhanced Winds:
    More flexible rendering of multi-channel winds, incorporates information on wind layers (16.x –> 16.4.1) GOES-R and Polar Products
  GeoDB:
    Configuration file controlled capability for ingest and display of geometry/attribute data (e.g., active fires or hurricane intensity estimates) where data are stored directly in A2 Database (16.x -> 16.4.1) GOES-R and Polar Products
  Enhanced Sounding:
    Adapt existing soundings with GOES-R (16.4.1)
Install TOWR-Repository to collaboratively implement A2 configurations, enhancement tables, and initial product use documentation
  Plugins / TOWR-Repo Provide Migration Path to Baseline

## Slide 6: GOES-R Product Pathway Summary
1. Sixteen Sectorized Cloud and Moisture Imagery Bands, (KPP), from GOES-R Ground System to, NCF uploaded to SBN to all AWIPS sites
  Status, Risks and Mitigations
    Software – Tested with simulated data
    Distribution – Tested with simulated data over SBN GOES-R channels to select sites
    Performance – Tested with simulated data
    Storage Capacity (WFOs only) - Issue to Meet “24 Hour Retention Requirement”
      Reduce retention for select products for DOE-4
      Requested Raytheon proposal to investigate near-term solutions for using existing architecture
    Training/Usability – Risks
      DOE-4 is an opportunity to test/evaluate of usability and provide feedback using 11 DOE-4 Use Cases
      Training Division developing training modules
2. PDA Standing Subscription at NCF to SBN to all AWIPS Sites for Lightning Detection and Derived Motion Wind Products
  Status, Risks and Mitigations
    Software – Tested with simulated data for Derived Winds, Lightning Detection testing in progress
    Distribution – Tested with simulated data on SBN experimental channel
    Performance – Tested with simulated data
    Training /Usability– Risk
      DOE-4 is an opportunity to test/evaluate of usability and provide feedback using 11 DOE-4 Use Cases
      Training Division developing training modules

## Slide 7: GOES-R Product Pathway Summary Continued
PDA-OGC Data Delivery for ~20 Derived Products used for on-demand weather scenarios
  Uses AWIPS WAN for site unique subscriptions
  Data Delivery SBN subscription channel for shared subscriptions
  Status
    PDA software and testing in progress, recent success in end-to-end tests on NHDA for most of the derived products
    ATAN to be used for PDA Data Delivery at DOE-4 sites
  Risks and Mitigations
    Distribution – Latency issue with current WAN Bandwidth
      WAN expansion (Dissemination Project) will not be in place for all DOE-4 sites
        Data Delivery Shared Subscription using SBN DD Channel
        SBN experimental channel
      WAN expansion for March 2017 Schedule Risk
    Training/Usability – Risks
      DOE-4 is an opportunity to test/evaluate of usability and provide feedback using 11 DOE-4 Use Cases
      Training Division developing training modules

## Slide 8: GOES-R Product Pathway Summary Continued
4. Direct Read-Out of all products for National Centers and select WFOs, e.g., PR
  NAWIPS – Requires McIDAS files as input
    ISatSS to convert to McIDAS format – Implementation - TBD
  NCP – A2 Plugins test and verification
    Test and evaluation in progress with NCO
  Training and Usability Risks
    DOE-4 is an opportunity to test/evaluate of usability and provide feedback using 11 DOE-4 Use Cases

## Slide 9: 2016 GOES-R Simulated Product Deployment Dates (Tentative)
Product
GOES-R Aerosol Detection*
GOES-R Aerosol Optical Depth*
GOES-R Sea Surface Temperature*
GOES-R Land Surface Temperature*
GOES-R Cloud Mask*
GOES-R Cloud Phase*
GOES-R Derived Motion Winds
GOES-R Snow Cover*
GOES-R Fire/Hot Spot Characterization
GOES-R Derived Stability Indices*
GOES-R Cloud Top Temperature*
GOES-R Cloud Top Height*
GOES-R Legacy Vertical Temperature Profile*
GOES-R Legacy Vertical Moisture Profile*
GOES-R Total Precipitable Water*
GOES-R Rainfall Rate/QPE*
GOES-R Volcanic Ash: Detection and Height
GOES-R Lightning Detection*
9
GOES-R Simulated
Products
Requires TOWR-Repo
(*) = provided over
Exp Channel Beginning
May 2016

## Slide 10: 2016 Satellite Product Operational Deployment Dates (Tentative)
Product | Provided over Exp Channel
SNPP VIIRS Imagery (CH M05 0.672 um) | May
GCOM AMSR-2 Sea Surface Wind Speed | May
GCOM AMSR-2 Microwave Imagery | May
GPM GMI Microwave Imagery | May
GPM IMERG-Early Calibrated Multi-Satellite Precipitation | May
GPM IMERG-Early Calibrated Multi-Satellite Precipitation Error | May
GPM IMERG-Late Calibrated Multi-Satellite Precipitation | May
GPM IMERG-Late Calibrated Multi-Satellite Precipitation Error | May
SNPP ATMS Total Precipitable Water | May
SNPP ATMS Rain Rate | May
Radarsat SAR Winds | May
Sentinel SAR Winds | May
SNPP VIIRS Active Fires | May
SNPP VIIRS Volcanic Ash | May
SNPP VIIRS Aerosol Detection | May
SNPP VIIRS Suspended Matter | May
SNPP VIIRS Aerosol Optical Depth | May
SNPP VIIRS Aerosol Particle Size | May
GOES-NOP Fog and Low Stratus | May
Himawari Derived Motion Winds | May
Himawari Cloud Top Height | May
Himawari Cloud Top Phase | May
Himawari Clear Sky Mask | May
GCOM Sea Ice Characterization (MIRS) | May
SNPP VIIRS Ice Concentration | May
SNPP VIIRS Sea Ice Characterization | May
SNPP VIIRS Ice Age/Thickness | May
SNPP VIIRS Ice Surface Temperature | May
Jason-2 Significant Wave Height | May
10
Schedule for Polar
Products
Requires A2 16.2.1
and TOWR-Repo

## Slide 11
Data Activation
Initiate early operational data flow, then migrate to Final Operating Posture
  Flow data prior to A2 “Baseline Release”
  Start with SBN Experimental Channel
  Use NWS IDP and/or NESDIS PDA to shape data for AWIPS Compatibility and minimum bandwidth
Transition to AWIPS-DD or SBN Ops Channel/Tailoring as appropriate based upon Feedback
11

## Slide 12
GOES-R Product Samples
12
Aerosol Optical Depth
Total Precipitable Water
Ch 14 Window IR (11.2 um)
Ch 14 Window IR (11.2 um)
Notes: The two images at top are for the same time with different color tables prepared by the Satellite Enhancement Team

## Slide 13
Polar Product Samples
13
S-NPP ATMS Total Precipitable Water
IMERG-Early ½-hourly Precipitation Accum

## Slide 14: AWIPS Data Delivery and PDA
What is AWIPS II Data Delivery?
  Data Delivery uses “smart” push/pull technologies to allow AWIPS-II users to access data not routinely delivered via the Satellite Broadcast Network (SBN)
  Enables AWIPS to handle increased data volumes associated with major agency initiatives, e.g., GOES-R, Higher resolution models, etc.
  Key Features
    Data discovery of datasets residing on data provider systems, e.g., NOMADS, MADIS, Product Distribution and Access (PDA)
    Data access using subscriptions or ad hoc requests to support specific/unique forecaster requirements (e.g., fire weather or winter storm)
    Users can temporally, spatially, and/or parametrically subset datasets
      Reduces bandwidth demands
      Reduces data processing at receiving AWIPS sites

## Slide 15: AWIPS Data Delivery and PDA
AWIPS Data Delivery and PDA Open Geospatial Consortium (OGC) Interface
  OGC interface supports data discovery, access and (on PDA system) sub-setting
Candidate Satellite Product Categories for Data Delivery PDA Interface
  GOES-R – Derived Products
    Note: To be assessed as part of DOE-4 exercise
  SNPP/JPSS Derived Products, non-KPP imagery
  GPM, SMAP, NESDIS PDA Products not distributed via SBN, Sentinel, MeTOP imagery, OceanSAT

## Slide 16: Data Delivery High Level Architecture

## Slide 17: Data Delivery Status and Plans
Current Status
  Data Delivery Installed at Regional HQs and Select WFOs including DOE-4 Sites (Baseline Functionality: NOMADS, MADIS)
AWIPS II Data Delivery – PDA for DOE-4 Support
  Successful end-to-end test of functionality completed between in testbed environment in February 2016
  Data Delivery with PDA Functionality to be ATAN’d to DOE-4 sites by June
  Issues/Risks
    Data Delivery depends on limited AWIPS WAN bandwidth. WAN upgrade (OneNWS) only planned to be completed at select DOE-4 sites (See NWS Dissemination Brief)
    Limited use and training of DD functionality thus far
  Mitigation
    Experimental channel on SBN used for most DOE-4 sites
    Data Delivery Team in Collaboration with Tower-S team to test and develop procedures and training for Data Delivery GOES-R product scenarios

## Slide 18: Sample GOES-16 Simulated Cloud Top Pressure Product CONUS sector subset over Florida Area - NHDA Testbed
200- 1000mb

## Slide 19: Questions