## Slide 1: CONOPS 2017: NWS Post-Launch Plans for GOES-R
Matt Seybold (OSPO/SPSD)
GOES-R Data Operations Manager
& PRO Team Lead
NOAA Satellite Proving Ground and User Readiness Meeting
May 9, 2016

## Slide 2: Ken asked – How does NWS IOC line up?
Internal Flow
L+15 Days
External Distribution
L+88 Days
Operations Handover
L+6 Months
East/West Assignment
L+12 Months
Instrument | Distribution Commences
ABI | L+88
EXIS | L+92
MAG | L+93
SUVI | L+104
SEISS | L+139
GLM | L+148
  NWS IOC for GOES-R

## Slide 3: Ken also asked – What is IOC for all baseline products (shown by Mike Johnson)?
Declaration of Maturity
Milestones occurs at
Peer-Stakeholder Product
Validation Reviews (PS-PVRs)
Internal Flow
L+15 Days
External Distribution
L+88 Days
Handover Readiness
Review (HRR) &
Operations Handover
L+6 Months
East/West Assignment
L+12 Months
  No later than L+6 Months

## Slide 4: Frank asked – Can we get data prior to L+88?
Internal Flow
L+15 Days
External Distribution
L+88 Days
Operations Handover
L+6 Months
East/West Assignment
L+12 Months
No. Only data flow testing activities prior to L+88.
Remember, GOES-East and GOES-West are still operational and GOES-14 is in standby.
Only one potential exception, with four criteria:
Hazardous event with certain impact to life and property
NWS shows GOES-R data are uniquely qualified to add value
NWS has tolerance for the caveats associated with uncertified data
No potential compromise to health & safety of satellite by pausing PLT

## Slide 5: When are data unavailable during PLT?
Internal Flow
L+15 Days
External Distribution
L+88 Days
Operations Handover
L+6 Months
East/West Assignment
L+12 Months
There is a notional Schedule of Events (SOE) for tests during the PLT phase
Between L+88 and Operations Handover, tests which will interrupt the flow of data will be announced via GOES-R notifications to NWS
After Operations Handover, interruptions will be communicated via ESPC Notifications

## Slide 6: BACKUP

## Slide 7: Data Release Strategy
  Ground Segment internal flow of instrument data: Commences upon completion of each instrument’s outgassing
  Data will flow for path integrity test purposes to PDA and AWIPS
  Data will flow for instrument vendor and CWG Cal/Val purposes to LZSS
  Data will not be released from LZSS, PDA, AWIPS to any other downstream consumers other than instrument vendors, CWG, and CLASS. The Unique Payload Services (GRB, HRIT/EMWIN, DCS) will also not yet distribute data.
  First media image(s) for ABI will be released after Orbit Raising and initial image navigation and radiometric assessment

## Slide 8: Data Release Strategy
External product distribution (PD): Commences upon completion of each instrument’s Post-Launch Tests (data will have Beta Maturity)
  Unique Payload Services [GRB, HRIT/EMWIN, DCS] will be populated
  LZSS, PDA, AWIPS will flow data to their respective, integrated, downstream consumers
  Estimated dates for completion of each instrument’s Post-Launch Tests:
    ABI @ L+88, EXIS @ L+92, MAG @ L+93, SUVI @ L+104, SEISS @ L+139, GLM @ L+148
Internal Flow

## Slide 9: Data Release Strategy
Operations Handover from GOES-R to OSPO: L+6 Months
Internal Flow
External Distribution

## Slide 10: Data Release Strategy
GOES-R Assignment to East or West Position: L+12 Months
Internal Flow
External Distribution
Operations
Handover

## Slide 11: Recap: Data Release Strategy
Internal Flow
L+15 Days
External Distribution
L+88 Days
Operations Handover
L+6 Months
East/West Assignment
L+12 Months
Instrument | Distribution Commences
ABI | L+88
EXIS | L+92
MAG | L+93
SUVI | L+104
SEISS | L+139
GLM | L+148

## Slide 12: Detailed Data Release Strategy
Declaration of Maturity
Milestones occurs at
Peer-Stakeholder Product
Validation Reviews (PS-PVRs)
Internal Flow
L+15 Days
External Distribution
L+88 Days
Handover Readiness
Review (HRR) &
Operations Handover
L+6 Months
East/West Assignment
L+12 Months

## Slide 13: Product Maturity Levels
What do the Product Maturity Levels mean? There is a PS-PVR at each stage as a method of informing the user community of the following readiness for use:
Beta: Products are made available to users to gain familiarity with data formats and parameters. It has been minimally validated and may still contain significant errors and is not optimized for operational use.
Provisional: Product ready for operational use but has documented known issues. Product analyses are sufficient to communicate product performance to users relative to expectations.
Full: Product is operational. All known product anomalies are resolved and/or documented and shared with the user community.

## Slide 14: What is a PS-PVR?
A Peer Stakeholder - Product Validation Review (PS-PVR) appraises the status of product quality with respect to Program definitions. The PS-PVR Panel has the authority to declare products have achieved a product maturity level and provides guidance on work expected to achieve the next maturity level.
Instrument
Vendor
Analysis (L1b)
CWG / AWG
Analysis
Declaration
Of
Product Maturity Level
Customer
Forums
(ABI L2+, including CMI, GLM L2+)
PS-PVR
Chair: Steve Goodman, GOES-R Program Scientist
Panel (consolidated recommendations to Chair): NOAA GOES Operational Requirements Working Group and GOES-R PSE
Presenters: CWG and AWG
Users: NOAA Line Offices (NWS, NOS, NMFS, OAR, OMAO)

## Slide 15: Focus during PS-PVRs
What will be the focus of the PS-PVR at the different maturity levels?
Beta:
Review present state of PLT activities and results
Consider initial product quick looks
Affirm release of data products to public
Provisional:
Review present state of PLPT activities and results
Compare initial assessment to predicted performance
Discuss user feedback, known anomalies, and remediation strategies
Recommend path to predicted performance
Full:
Review present state of continuing cal/val activities and results
Compare ongoing assessment to predicted performance
Recommend further optimization activities, considering mission parameters and priorities
Affirm dissemination of product quality assessment to public

## Slide 16: Tentative PS-PVR Schedule Given 10/13 Launch

## Slide 17: PLPT Science Validation Success Criteria: Determination
GOES-R LIRD, MRD, PORD Requirements
Instrument Design, Fabrication, and Test
Instrument Performance
Model Analysis to Predict On-Orbit Product Performance
GOES-R CONOPS
Defined PLPT Analysis Methods and Val Reference Data Spatial/Temporal Coverage Limits (in RIMPs)
PLPT Analysis to Determine On-Orbit Product Performance
Comparison between determined and predicted on-orbit product science performance
GOES-R Post-Launch Validation:
The process of determining that the deliverable item satisfies its intended use in its intended environment. A post-launch re-certification of pre-launch predicted performance.
GOES-R Pre-Launch Verification:
The process of determining that the deliverable item meets specified requirements, using methods such as test, demonstration, analysis, and inspection.
BASELINE

## Slide 18: First Public Image Release

## Slide 19: First Public Image Release
The first public image of ABI will be notionally released 61 days after launch.
  The following tentative criteria must be met before image release:
    Full disk image navigation and radiometric accuracy is qualitatively acceptable (e.g., no inversion, minimal striping, no clear saturation)
    Visibly free of non-physical artifacts
    Image is captured during local daylight hours with significant discernible geographic features (e.g. moderate cloud cover)
    All 16 channels meet above criteria
    No open flight (spacecraft or instrument) or ground incident reports preventing instrument readiness for first image broadcast
    Vendor and science teams GO
    Program and project management GO
  Data mock-ups are in hand and now turning to Outreach Coordinators for story-board layouts and PLT release plan

## Slide 20: Questions?