## Slide 1
NOAT Perspective on STAT
Bill D. Ward
Pacific Region Headquarters, NOAA/NWS
Honolulu, HI

## Slide 2: STAT Background
NOAT/OCLO Team discussed last year in June
SOOs brought together at the SOO/DOH conference Sept 2015
Team formed and met October 2015
Follow on Meeting Feb 2016
  Module development began April 2016
  Modules to be completed Sep 30, 2016
  Formal rollout Oct 1, 2016

## Slide 3: Stat Module Categories
GOES-R Introduction and SatMet background
  Three modules
ABI
  Five modules
Baseline Subsection
  Seven modules
Geostationary Lightning Mapper
  Two modules
Phenomenologically-based lessons (mesoscale and synoptic features)
  17 modules
NWP Assimilation
  Three modules
Exercises
  Two modules

## Slide 4: Pre-requisites to Short Course
Each course participant should have completed the following modules in the Foundational Satellite Training Course (FC) prior to attending the short course (approx. 2.0 hours, total)
  Basic Principles of Radiation
  Basic Operation of GOES­R
  Spectral Bands I (vis)
  Spectral Bands II (NIR)
  Spectral Bands III (other IR)
  Spectral Bands IV (WV).

## Slide 5: GOES-R DAY-1 READINESS
Lead:
John Ogren, Acting CLO, OCLO and Bill Ward ESSD Chief, PR
Scope:
. Prepare for GOES-R Day-1 Readiness
Estimated Benefits:
  1.) Ensure everyone is ready for GOES-R on March 1, 2017 (IOC)
  2.) Final Operating Capability (Reaches final resting point)

## Slide 6: Short Course Timeline

## Slide 7: Risks/Issues
  Issues:
  - Resources – Travel Cap
  - Data – Using synthetic data with TOWR-S to emulate GOES-R
  - AWIPS storage – Additional disk space is a requirement
  Mitigation:
  Plan/manage through the AOP process
  Satellite Information Familiarization Tool (SIFT) to be used for GOES-R short course and incorporated into NWS offices to support operations.
  Working with CP(AWIPS) for a solution for the storage space

## Slide 8
Milestone | Date | Status
Satellite Training Advisory Team (STAT) (GOES-R foundational Modules being developed) | Q4 | On track
Satellite Enhancement Team (SET) (Development of color tables using full bit depth) | Q4 | On track
TOWR-S (Testing has begun - anticipating operational by IOC) | Q4 | On Track
Short Course for SOOs/DOHs (Satellite Information Familiarization Tool for GOES-R) | Q2 FY17 | Completion date March 1st
Deliver and Initiate Sat FC-G by 30 Sept 2016 (All Modules will be published by this date) | Q1 FY17 | On track

## Slide 9: Questions
Contact
Bill Ward
ESSD Chief, PRH
bill.ward@noaa.gov
808.725-6010