## Slide 1: GOES-R Cal/Val
Bob Iacovazzi GOES-R Cal/Val Coordination Team (CVCT) Lead
February 23, 2015

## Slide 2: Outline
Cal/Val Roles and Responsibilities
  Pre-Launch Instrument-Level Cal/Val Test Data Analysis
  Post-Launch Test (PLT)/Post-Launch Product Test (PLPT) Objectives and Plans
Pre-Launch PLT/PLPT Readiness Activities
  Proxy datasets for Data Operations Exercises
  HIMAWARI-8 AHI cal/val analysis
PLT/PLPT Activities
  Validation maturity indices, success criteria, and expected outcomes

## Slide 3: Cal/Val Roles and Responsibilities
CVCT
Management
Cal/Val Teams
CWG (STAR, NGDC, MSFC, etc.)
AWG (STAR, MSFC)
OSPO (Radiometric and INR Engineers
and Product Area Leads)
Flight, DOST &
GOES-R Vendors
(ATC, Exelis, LASP, LM)
Stakeholders
NWS, AFWA, etc.
Stakeholders
Integrate GOES-R data into their forecast systems
Provide feedback from validation efforts
Cal/Val Coord. Team (CVCT) Management
Coordinate all GOES-R cal/val efforts
Manage cal/val resources, schedules, milestones, and risks
Support Customer/User community
Cal/Val Teams
Provide test objectives and plans
Create and test off-line monitoring and analysis tools
Monitor and analyze data products
Provide testing reports
Participate in anomaly resolution
GOES-R Vendors
Deliver instrument and GS that meet Contractual specifications
Support pre- and post-launch cal/val efforts
Flight and DOST
Carry out pre- and post-launch system-level Observatory and GS Testing

## Slide 4: Pre-Launch Instrument-Level Cal/Val Test Data Analysis
  No showstoppers have been discovered that would prevent vendor shipment of any FM-1 instrument to the Gov’t
Vendor cal/val reports, supporting activities and calculations have been independently reviewed for all GOES-R Flight Model-1 (FM-1) instruments by members of the Gov’t Cal Working Group (CWG) from MIT/LL, NIST, NASA, and NOAA
Notes: No Showstoppers – Either analysis showed that the instrument meets requirements, or requirements waivers and their impacts on products were deemed acceptable by the Government.

## Slide 5
PLT/PLPT Test Objectives & Plans
Cal/Val Strategy & Tech Plans
Product Val Maturity Stages
Program- and Project-Level Val Objectives
PLT Engineering Review Board
GORWG, NOAA Indep. Advisory Committee
Instr. Cal PLT
Product Science Val PLPT
Final PLT Test Forms
Final PLPT Plans
Validation Implementation
Draft PLT Test Forms
Draft PLPT Plans
Draft Test Objectives and Plans
Approve Test Plans
Pre-Launch Prep
Pre-Launch Testing
Data Accessibility & Monitoring and Analysis Software Tool Tests (Simulated and S/C TVAC Test Data)
PLT Command Procedure Tests (SatSim)
CWG/AWG (PLPT analyses and reporting), MOST (Observatory commanding), GRT (GS Ops support)
Flight Vendor (PLT analyses and reporting) & CWG(review), MOST (Observatory commanding), GRT (GS Ops support)
Post-Launch SPOT

## Slide 6
Cal/INR/Product Science (CIPS) Val Tool Development
4 months
6 months
12 months
Mission Operations Review (MOR) and System Integration Review (SIR)
Flight Operations Review (FOR)
9 Months
CIPS Val Tool Testing
Post-Launch Test (PLT) Planning/ Preparation & System-Level Test Planning/Implementation
Cal&INR PLT Procedure Development
ETE I-V Testing
DOE
Cal&INR PLT Definition
Data Operations Exercise (DOE) Planning & Ground Segment Training
CIPS Val Maturity Stage Definitions
Launch
Post-Launch Product Test (PLPT) Definition and Development
CVCT Kick-Off
Sep13
MOR - Jun 14/ SIR - Jul 14
Jul15
Mar16
CIPS Concept of Operations (CONOPS) and Operational Concept (OPSCON) Development
CIPS OPSCON Rehearsals
Pre-Launch PLT/PLPT Readiness Activities
  Plan observatory post-launch tests (PLT)
  Plan data post-launch product tests (PLPT)
  Complete Cal/Val analysis tool development, testing, and implementation
  Define PLPT Cal/Val quality monitoring, analysis, and anomaly resolution Operational Concept rehearsals, and implement them during Data Ops Exercises (DOEs)
  Train relevant Cal/Val personnel to use Core Ground Segment capabilities
Notes: Pre-launch GOES-R cal/val activities. Primary focus is “Day-one Readiness” for GOES-R observatory post-launch tests and data post-launch product tests.

## Slide 7: Pre-launch Cal/Val Test Data Resources (1 of 2)
CVCT Validation Item | L0 Inputs | L1b Inputs | AHI Data
L1b Product and Instrument Calibration Data science content |  |  | 
L2+ Product science content |  |  | 
Product Generation (PG) Product Performance Monitor (PPM) science content and usability |  |  | 
Mission Management (MM) Product Monitor (PM) science content and usability |  |  | 
Development Environment usability for cal/val analysis |  |  | 
Computing resources; data storage systems; and PDA, LZSS and CLASS network connectivity |  |  | 
Cal/val monitoring and analysis software tools |  |  | L2+
Cal/val OPSCON |  |  | 
DOE/GSIT Data INPUT
MVT-DS S/C TVAC L0 Data (ETE-3)
AAWDS Simulated L1b Products
BDS, MVT-DS & EDS Simulated L0 Data

## Slide 8
Reference Validation Data are available from:
U.S. owned operational and research satellites
International satellite programs with data sharing agreements in place
NOAA funded in-situ measurement platforms
Pre-launch Cal/Val Test Data Resources (2 of 2)

## Slide 9: GOES-R & JMA AHI Collaboration
GOES-R ABI Radiance Product Validation Team Analysis
    Analyze AHI on-board calibration data: Including solar diffuser, blackbody, and spaceview data taken during calibration, and supporting data needed to determine instrument calibration coefficients
    Analyze AHI lunar data for the purpose of radiometric trending and MTF analysis
    Compare AHI L1b data with radiometric measurements from other operational polar and geostationary imagers
GOES-R ABI L2+ Product Validation Team Analysis
    Process AHI L1b data using the GOES-R L2+ product algorithms as applicable
    Compare AHI L2+ products with those derived from applicable reference/ground truth observations from other observing platforms (e.g., similar products derived from polar orbiting and geostationary imagers; ground-based observations, etc)
  GOES-R Product Operations
    Share ground segment operational concepts for AHI and ABI calibration, image navigation and registration (INR) and product science performance monitoring, analysis and anomaly resolution

## Slide 10
LEGEND
Launch & Orbit Raising
Operations -
Post-launch Testing (PLT) - 180 Days
Outgas
System Performance Operational Test (SPOT)
12 Days
30 Days
60 Days
6 Mo
Post-Launch Assessment Review (PLAR) and Handover Readiness Review (HRR): Handover S/C Ops to OSPO
30 Days
PLPT
Ex-tended Val
<=5yrs Storage + >=8.4 Yrs Ops
Beta Stage Testing
Provisional Stage Testing
Validated Stage Testing
Peer-Stakeholder L1b & KPP Product Validation Review
Handover L1b & KPP Products to NWS
Peer-Stakeholder L2+ Product Validation Reviews
Handover L2+ Products to NWS
L+70Days
PLT End + 15Mo
ABI (L1b&CMI)
ABI (Other L2+)@
GLM (L2+)
SpWx (L1b)@
Products Not Yet Available to Public
Beta Validated Product
Provisionally Validated Product
Fully Validated Product
L+192Days
PLT Cal/INR
32 Days*
28 Days
L+87Days
L+ 86(MAG), 95(SUVI), 107(EXIS), 130(SEISS) Days
L+192Days
PLT End + 4Mo
L+103Days
L+139 Days
L+77Days
L+73Days
@ Maturity level may vary for each product, as product availability is driven by maturity of
algorithm implementation, as well as, the existence of science phenomena and associated ground-truth data.
9 Mo
PLT End + 12Mo
PLT End + 12Mo
PLT End + 12Mo
L+70Days
PLT/PLPT Activities
* Data blackout due to Storage Mode Ops and Station Change to 105W.
Notes: Post-launch GOES-R cal/val activities. The top bar illustrates the GOES-R post-launch mission phases – Launch and Orbit Raising, Post-Launch Testing, and Operations. The Post-Launch Testing period includes a traditional observatory checkout, but also contains a period of Post-Launch Product Tests (PLPTs) designed for limited product quality assessment before Spacecraft Handover. After Handover, a period of Extended Validation is planned to enhance product science validation maturity. The colored lines in this figure represent the validation maturity stages of each product family – ABI L1b and Cloud and Moisture Imagery (CMI), ABI Other L2+, GLM L2+, and Space Weather L1b – and their association with post-launch mission phases. In this post-launch scenario, by Spacecraft Handover the expectation is that all L1b products and CMI will be Provisionally Validated, while all other products will be Beta Validated.

## Slide 11
GOES-R Product (L1b and L2+) Validation Maturity Stage End States
Beta Validated | Product is minimally validated, and may still contain significant errors (identified and unidentified). Information/data from validation efforts can only be used to make initial qualitative and/or very limited quantitative assessments regarding product fitness-for-purpose. Documentation of product performance and identified product performance anomalies, including recommended remediation strategies, exists.
Provisional Validated | Product performance (L1b or L2+) has been demonstrated through analysis of a large, but still limited (i.e., not necessarily globally or seasonally representative) number of independent measurements obtained from selected locations, time periods, or field campaign efforts. Product analyses are sufficient for qualitative, and limited quantitative, determination of product fitness-for-purpose. Documentation of product performance, testing involving product fixes, identified product performance anomalies, including recommended remediation strategies, exists. Product is ready for potential operational use (user decision) and for use in scientific publications after consulting product status documents.
Fully Validated | Product performance has been demonstrated over a large and wide range of representative conditions (i.e., global, seasonal). Comprehensive documentation of product performance exists that includes all known product anomalies and their recommended remediation strategies for a full range of retrieval conditions and severity level. Product analyses are sufficient for full qualitative and quantitative determination of product fitness-for-purpose. Product is ready for operational use based on documented validation findings and user feedback. Product validation, quality assurance, and algorithm stewardship continue through the lifetime of the instrument.

## Slide 12: PLPT Validation Event (VE) Success Criteria
GOES-R LIRD, MRD, PORD Requirements
Instrument Design, Fabrication, and Test
Instrument Performance
Model Analysis to Predict On-Orbit Product Performance
GOES-R CONOPS
Defined PLPT Analysis Methods and Val Reference Data Spatial/Temporal Coverage Limits
PLPT Analysis to Determine On-Orbit Product Performance
Comparison between determined and predicted on-orbit product science performance
GOES-R Post-Launch Validation:
“The process of determining that the deliverable item satisfies its intended use in its intended environment”
GOES-R Pre-Launch Verification:
“The process of determining that the deliverable item meets specified requirements, using methods such as test, demonstration, analysis, and inspection.”

## Slide 13: PLPT Validation Outcomes
Validation teams communicate product science performance to stakeholders through Peer-Stakeholder Product Validation Reviews (PS-PVRs)
Scope and success criteria of information and analysis presented in the PS-PVRs is bounded by the objectives of each validation stage – e.g., provisionally validated L1b for operational Handover.
Validation teams submit product performance artifacts or anomalies to the algorithm change process, which prioritizes the changes according to severity of impact to the Program objectives.

## Slide 14: Summary
GOES-R Cal/Val is a multi-disciplinary, multi-agency and geographically dispersed collaboration
Thorough pre-launch instrument cal testing assessments have been performed by Vendor and Gov’t SMEs before instrument shipment
Intensive PLT/PLPT planning and preparations are underway and are subject to independent review
Pre-launch rehearsals are being developed that includes test data sets needed for Cal/Val Day-One Launch Readiness
The expectations of PLT/PLPT and associated GOES-R Product Handover are being defined and vetted with Stakeholders

## Slide 15
Backup Slides

## Slide 16
CVCT Val Teams
ABI Radiometrics (Lead: Xiangqian Wu)
Technical Analysis: CWG
Support: Flight, GSP, ABI Vendor & NWS)
ABI/GLM INR (Leads: Tim Schmit and Dennis Buechler)
Technical Analysis: CWG
Support: Flight, GSP, NWS & ABI/GLM Vendors
Space Weather Products (Lead: Bill Denig)
Technical Analysis: CWG
Support: Flight, GSP, NWS, and Sp. Wx. Instr. Vendors
L2+ Products* (Lead: Jaime Daniels)
Technical Analysis: AWG
Support: Flight, GSP, & NWS
Transition Team: CWG
Transition Team:
N/A
Transition Team: N/A
Transition Team: N/A
*Teams based on product areas listed in Cal/Val Plan Volume 2
Staff Located at Site External to GS
Staff Located at Core GS Site
Support: OSPO, MOST, GSIT/DOST & GS and Instr. Vendors

## Slide 17: Post-Launch Testing (PLT) vs Post-Launch Product Testing (PLPT)
Perform observatory activation and calibration
Demonstrate that instrument and spacecraft performance related to key L3 requirements has not degraded due to launch and on-orbit environment (Level 1B product centric)
  Demonstrate key functionalities not demonstrated in activation or normal operations (mission operations scenarios)
  Testing plans approved by the PLT Engineering Review Board
Provide Stakeholders with a snapshot of product science performance before observatory Handover
Analyses utilize nominal operational instrument calibration and science data modes
Program MRD and CONOPS used as a guide to determine scope of testing
Validation Event Plans approved by the GORWG and NOAA IAC
PLT supports creation of an on-orbit baseline for key product performance parameters (e.g. – noise)
PLPT product inspections and comparisons with ground truth can be used to assess calibration, INR/pointing, and L1b product performance
  Observatory PLT
PLPT

## Slide 18: Test Datasets Summary
Data Set | Type | Provider/Source (Description)
Baseline Data Set (BDS) | Consultative Committee on Space Data Systems (CCSDS) | Instrument Vendors (Simulated L0 data) Algorithm Working Group (Simulated L1b data) Harris (L0/L1b data modified to run through GS)
Mission Validation Test Data Set (MVTDS) ETE-3 Spacecraft T-Vac | Channel Access Data Unit (CADU) | Spacecraft Vendor (L0 data as it would be sent from the spacecraft)
MVT-DS Simulated L0 Data | CCSDS | PSE/MIT (Expanded BDS L0 data)
Errors Data Set (EDS) | CCSDS | GOES-R Data Engineering Group (BDS/MVTDS L0 data with dropped bits and missing packets)
ABI AWG/UW Data Set (AAWDS) | CCSDS | Algorithm Working Group / University of Wisconsin (Simulated ABI radiance data that can be generated near real-time)

## Slide 19: AAWDS Data Sets
Nominal / non-nominal / or both – Nominal (no noise/artifacts)
Delivery method (FTP, DVD, DSS, .. ) – FTP (ftp://ftp.ssec.wisc.edu/ABI/REALTIME_PROXY/DOST/)
Source (Science basis): GOES-R AWG Proxy Data Team WRF-CHEM/GFS/CRTM based proxy radiances for all 16 ABI bands
  Fidelity –WRF-CHEM CONUS E/W are high fidelity (realistic surface and clear sky radiances, Thompson microphysics for cloud diameters, WRF-CHEM GOCART aerosols, validated with GOES Sounder radiances), GFS Full Disk E/W are medium fidelity (realistic clear sky radiances, GFS cloud diameters, currently no aerosols and CRTM default surface reflectances/emissivities)
  Interdependencies –spectral and grib2 GFS forecasts, RAQMS aerosol/ozone forecasts, 16-day MODIS BRDF, WF-ABBA fire detection
  Limitations – WRF-CHEM CONUS at native 8km resolution, high bias for cold clouds, GFS Full Disk at native T574 (28km), radiances have not been validated
  Time/Duration – Daily 24hr (12Z-12Z) duration, WRF-CHEM CONUS at 1hr frequency, GFS Full Disk at 3hr frequency
When available initially and any updates – Currently available, GFS Full disk will be updated to improve fidelity
Provider organization – NOAA/NESDIS/STAR, UW-Madison CIMSS
Status of dataset development (i.e. complete, in-work, etc. ) – initial delivery completed and producing daily products, plan to add RAQMS aerosols and improved surface reflectivity/emissivity to GFS Full Disk, plan to add MODIS and WF-ABBA fire detections