## Slide 1: NOAA/NWS Satellite Training Plan
LeRoy Spayd,
NOAA/National Weather Service
Office of Chief Learning Officer (OCLO)
Anthony Mostek,
Chief, Forecast Decision Training Division (FDTD)
Brian Motta, OCLO/FDTD
Ed Mahoney, Chief, OCLO/WDTD

## Slide 2
NOAA/NWS Satellite Training Plan
Contributors
John Ogren OCLO/ CLO
Regional Scientists
Satellite Liaisons
JPSS, GOES-R
SOOs
Coop Institutes: CIMSS, CIRA, CIMMS
COMET
SPoRT and others

## Slide 3
NOAA Satellite Proving Ground engages NWS in pre-operational demonstrations of selected next generation capabilities.
The Proving Ground accomplishes its mission through:
        Sustained interaction between developers & users
        Training
        Product evaluation
        Solicitation of user feedback
        Product Improvement
        New Science and Technology Infusion
NOAA Satellite Proving Ground

## Slide 4
Roles and Responsibilities
Sat Training Stakeholders | Pre-Training Roles | Core Training (oper. data available first 6 months?) | Post Training – Continuous Learning | Notes
NWS Director | Set Agency Wide Goals, Announce High Priority, Review/Announce Plans @ SOO/DOH? | Review Progress Reports from PPA/Regional Directors | Review Completions, Report to NOAA Review Follow on Training | Uses Impacts on Operations for Future resource requests
NWS OCOO | Set Agency Wide Goals, Announce High Priority | Review Progress Reports from Regional Directors | Reports on Progress to Director | Provides Impact on Operations to Director
PPA Directors (OBS, CP, Diss, STI) | Set Agency Wide Goals, Provide & Test Data Delivery Plans, Announce High Priority | Provide Access Data/Products ASAP, Review Progress Reports from STI/OCLO | Review & Fund, Continuous Training | AWIPS2, Data Delivery, PDA, Comms, GRB (at Centers)
AFS, RDs, NCEP Directors | State priority of Satellite Training, Link to Excellence of Service (WRN), Ensure Office Progress Reports Submitted | Ensure Offices Report Progress | Report Success Stories, Review Evaluation Reports, Support/Review Follow on Training | 
OCLO Director | Prepare Agency-wide Goals, Announce High Priority | Prepare Progress Reports from Regional Directors | Prepare Completions Report, Support Continuous Learning, Review Status Training | 

## Slide 5
SSDs | Assist with Satellite Training Outreach Review Satellite Milestones & Satellite Training Implementation Plan | Set office training expectations for SOOs within their Region | Monitor feedback and evaluations to adjust ongoing Just-In-Time Training Plans
WDTD, FDTD Managers | Gather materials, Develop Training Conduct orientation with stakeholders Develop and Prepare for Training Phases 1 to 5 | Deliver Training Collect Evaluations Track Progress | Collect Level 3 Evaluation Conduct follow on: Simulations, Webinars
SOOs/DOHs | Participate National SOO/DOH Workshop Review & provide feedback Implementation Plan Participate in regional group(s) | Facilitate in office Sat Training Schedule course briefings w/staff Brief MIC/HIC on student perf. Report Best Practices & Need for Updates | Support Level 3 Evaluations Meet with staff plan follow on training – simulations, webinars, blogs, quick guides, etc.
CIMSS, CIRA, COMET, SPoRT | Prepare Satellite Training Agency wide – Support Testbeds and PG | Conduct, Track and Evaluate Training | SME and training support for event of the week, science infusion week, realtime access to satellite experts, follow-on course improvements
Roles and Responsibilities

## Slide 6
NESDIS Managers | Provide Funding, Prepare Agency Wide Goals, Provide Data Delivery Plans, Announce High Priority | Provide Access Data/Products ASAP, Review Progress Reports from NWS Directors | Review NOAA Completions – Report to NOAA Review & Fund Follow on Training | AWIPS2, Data Delivery, PDA, Comms, GRB (at Centers)
Supervisors Sat Liaisons | Provide Funding (GOES-R/JPSS) CI Manager Onsite Manager (NCs, OPG) Support role of liaisons in course development. | Provide resources to Liaisons to support local and national training plans Support for liaison training activities | Continue support for Just-in-time-Training Support for liaison training activities | 
Sat Liaisons See row above for multiple supervisors | Prepare and Conduct NC, Testbed and Ops PG Training - Include Himawari & SNPP Provide support to FDTD, WDTD in developing GOES-R core course | Update and Conduct NC, Testbed and Ops PG Training with GOES-R Training SME support. | Event of the week, science infusion week, realtime access to satellite experts, follow-on course improvements Assist in Just-in-time-Training for national ongoing plan | Managers Provide Support for Core Course components Support during continuous learning
Roles and Responsibilities

## Slide 7: Satellite Training Timeline (Updated)
Pre-Req
Foundational
Cont.
Learn
  Basic Remote Sensing
  Characteristics of Satellites
  Pull together from COMET, VISIT, CIMSS, CIRA, SPoRT, WMO Vlab, etc.
NWS-Specific development
Initially DNB & NUCAPS
GOES-GOES-R
Use Himawari, MSG & SNPP as examples
Geo vs Polar
Strengths & Weaknesses
FY15
FY17
JPSS Launch
FY16
GOESR Launch
Application
Exercise
Make it
Stick
Forecast/ warning process
Phenomena based
GOES- R Baseline & JPSS Operational products & NWS approved RGB’s.
Service areas (severe, winter, hydro, tropical, fire, aviation, etc.)
10-15 minute modules
Techniques
Quick Guides
Simulations
Local training initiatives
“As it occurs” training
Evolve initial satellite concept of operations
Reference materials in AWIPS
Repeat…practice
Blogs
Seasonal readiness
Peer-to-peer sharing
Storm-of-the month webinars
Demonstrated performance
Continuous Learning
Operations to Research
Optimize implementations for operations
Update for evolving science
Put in IDSS and WRN context
FY18 & Beyond

## Slide 8: Satellite (GOESR) Training Timeline
FY15
FY17 & Beyond
FY16
Launch
Application
Prerequisites
Making it
Stick
Data?
Foundation
Exercise
Continuous Learning
Training stages
Prerequisites – overall basics
Foundation – satellite specifics
Application – operational setting
Exercise – simulations, practice
Making it Stick – multi-situational, sharing
Continuous Learning – evolve and update

## Slide 9: Satellite (JPSS) Training Timeline
FY16
FY18 & Beyond
FY17
Launch
Application
Prerequisites
Making it
Stick
Foundation
Exercise
Continuous Learning
Training stages
Prerequisites – overall basics
Foundation – satellite specifics - SNPP Underway
Application – operational setting
Exercise – simulations, practice
Making it Stick – multi-situational, sharing
Continuous Learning – evolve and update

## Slide 10: NOAA/NWS Satellite Training Plan
Learning Goals
Understand differences between legacy GOES & GOES-R
  and SNPP/JPSS satellites
Use GOES-R & JPSS for NWS forecasts and warnings
Utilize satellite-based total lightning detection sources in forecast & warning operations (GLM, VIIRS, LIS)
Understand fundamental RGB satellite techniques &
  applications

## Slide 11: NOAA/NWS Satellite Training Plan
GOES-R Performance Objectives
Without references, in accordance with the training, and given GOES-R satellite data, demonstrate ability to:
identify convective initiation.
accurately estimate updraft strength and severe storm potential including:
  overshooting top characteristics
  presence of an enhanced-V
  anvil shape vs. storm-relative anvil-layer flow
  anvil top temperatures
issue effective warnings.
provide effective decision support services.
interpret GLM data and potential storm intensification.

## Slide 12
Foundational Training
WSR-88D
AWIPS-2
MRMS
Satellite
DLOC
AWOC
Core WDM
Warning Decision Making
Training
AWOC
Severe
AWOC
Flash Flood
AWOC
Winter Wx
Office
Warning Performance
- LMS
- WES-2 Bridge
- SOO/DOH Facilitation Workshop
- Storm of the Month
- Distributed Simulations
Warning Decision Making Training
Performance Pyramid

## Slide 13: Satellite (GOESR) Training Timeline
FY15
FY17 & Beyond
FY16
Launch
Application
Prerequisites
Making it
Stick
Data?
Foundation
Exercise
Continuous Learning
Topics: Basic Remote Sensing, Characteristics of Satellites
Who: COMET, SPoRT, CIMSS, CIRA, Liaisons, SOOs, …
What: Best examples of existing materials, infomercials?
Where: Various Web Sites, new NWS CLC
When: Dec 2015
Prerequisites

## Slide 14: Satellite (GOESR) Training Timeline
FY15
FY17 & Beyond
FY16
Launch
Application
Prerequisites
Making it
Stick
Data?
Foundation
Exercise
Continuous Learning
Foundation
Topics: NWS-specific development, GOES vs GOES-R, Geo & Polar, strengths and weaknesses
(Himawari, MSG & SNPP examples), Quick Guides
Who: OCLO, COMET, SPoRT, CIMSS, CIRA, Liaisons, SOOs, …
What: Repurpose existing modules
Where: NWS CLC
When: May - Sept 30, 2016? (data operationally available)

## Slide 15: NOAA/NWS Satellite Training Plan
Fundamentals:
Launch Ready: Awareness of data, products, training
  1 - 2 minute video series
  PAO “5 things you should know about (GOES-R or JPSS) ”
  GOES-R Fact Sheets
GOES-R & SNPP/JPSS Basics:
  Introduce new ABI & GLM capabilities, SNPP (NUCAPS, DNB)
  Satellite remote sensing science & engineering
  Current geostationary and polar satellite comparisons
  NWP data assimilation, anticipated benefits/impacts
  NWS forecaster & AWIPS focused

## Slide 16: Satellite (GOESR) Training Timeline
FY15
FY17 & Beyond
FY16
Launch
Application
Making it
Stick
Data?
Foundation
Exercise
Continuous Learning
Prerequisites
Application
Topics: Forecast/ warning process, phenomena-based, baseline products,
multi-service areas (severe, winter, hydro, tropical, fire, aviation),
10-15 minute modules, highlight techniques, provide Quick Guides
Who: OCLO, COMET, SPoRT, CIMSS, CIRA, Liaisons, SOOs, …
What: Quick Guides, short 5-15 minute modules
Where: AWIPS2 and NWS CLC
When: March 2017? – (GOES-R Operational East or West?)

## Slide 17: NOAA/NWS Satellite Training Plan
Learning & Performance Job Aids
Forecast & warning process applications
Satellite-based feature detection & analysis
Satellite-based warning guidance
Decision aids for interpretation & conceptual models
Optimal AWIPS displays & training guides
Best practices and methodologies
Strengths & limitations
Seasonal refresher training events

## Slide 18: Satellite (GOESR) Training Timeline
FY15
FY17 & Beyond
FY16
Launch
Application
Making it
Stick
Data?
Foundation
Exercise
Continuous Learning
Prerequisites
Exercise
Topics: Simulations, local training initiatives, “as it occurs” training,
evolve initial satellite concept of operations
Who: OCLO, COMET, SPoRT, CIMSS, CIRA, Liaisons, SOOs, …
What: WES2 simulations
Where: AWIPS2
When: March 2017 - GOES-R Operational?

## Slide 19: NOAA/NWS Satellite Training Plan
Applying GOES-R & JPSS data in NWS forecast & warning operations
Weather Event Simulator (WES)
1: Imagery interpretation & environmental situational awareness
(including 1-minute imagery)
2: GLM and total lightning data in forecast & warning processes
3: GOES-R and JPSS algorithm products (Fog Low Stratus, Convective
Initiation, etc.) in forecast process (diagnosis and forecast preparation)
GOES-R & JPSS Operations (Core):

## Slide 20: Satellite (GOESR) Training Timeline
FY15
FY17 & Beyond
FY16
Launch
Application
Making it
Stick
Data?
Foundation
Exercise
Continuous Learning
Prerequisites
Making it Stick
Topics: AWIPS references, repeat/practice, seasonal readiness, blogs, peer- to-peer sharing, storm-of-the-month webinars, demonstrated performance, O2R, science infusion week, evolve with science, put IDSS and WRN into context
Who: OCLO, COMET, SPoRT, CIMSS, CIRA, Liaisons, SOOs, …
What: Blogs, peer-to-peer sharing, storm-of-the-month webinars
Where: Websites, AWIPS2, NWS CLC
When: March 2017 thru 2018, … (JPSS/GOES-S launch/checkout)

## Slide 21: NOAA/NWS Satellite Training Plan
Event of the Week/Month:
Webinar promotes sharing of events/best practices
Participation & collaboration with experts (R2O, O2R, R2A)
Focus on interpretation of satellite data utilizing real events
Builds credibility & understanding among forecasters
Accomplished by leveraging expertise and satellite liaison
Note: Modeled after highly successful radar training
Dual-pol “Storm of the Month”.

## Slide 22: NOAA/NWS Satellite Training Plan
Science Infusion Week (Residence):
Goal: emphasize emerging science & satellite meteorology
Graduate-level Science Infusion Workshop
Target audience: SOOs/DOHs/Local Satellite Experts
Integrate satellite data & products in operations
Improves scientific quality of NWS WRN message
NCEP numerical models with new satellite data assimilation

## Slide 23: Satellite (GOESR) Training Timeline
FY15
FY17 & Beyond
FY16
Launch
Application
Making it
Stick
Data?
Foundation
Exercise
Continuous Learning
Prerequisites
Continuous Learning
Topics: Migrate new techniques learning in research/national centers to Operations, Seasonal readiness, optimize operational implementation, update with science, services, user feedback
Who: R2O and O2R
What: Blogs, peer-to-peer sharing, storm-of-the-month webinars, …
Where: AWIPS2, NWS CLC, websites
When: Start in 2017 - Continues through GOES-S & JPSS…

## Slide 24: Summary
NOAA satellite training - Focused on Forecaster
Collaborators: OCLO, Region Scientists, SOOs, Coop Institutes, COMET, SPoRT, Liaisons, GOES-R, JPSS
Integrates GOES-R & JPSS into NOAA/NWS Weather Ready Nation Program
NOAA Target Audience: 3000+
Uses Blended Continuous Learning: multi-mode training, on-line, in-person & on-the-job