## Slide 1
NOAA Proving Ground / User Readiness Meeting
AWIPS Readiness
Steve Schotz and Ed Mandel
June 16, 2015

## Slide 2: Agenda
AWIPS II Migration Status
  WFOs
  NCEP NAWIPS Migration
AWIPS II Satellite Product Readiness
  GOES-R Products
  Non-GOES-R Products
AWIPS II Data Delivery Readiness

## Slide 3: AWIPS II Migration Status and Plan
AWIPS II Deployed at all National Centers, River Forecast Centers and Regional HQ Systems
WFO AWIPS II Deployment Status
  AWIPS II deployed 104/120 WFOs as of 6/12/15
  On schedule to complete deployment before end of September
National Centers AWIPS (NAWIPS) Migration
  Center by Center FOTE strategy
  NAWIPS legacy will have to support new satellite products until migration is complete

## Slide 4: NWS Satellite User Readiness GOES-R Key Performance Parameter (KPP) Products
Product Summary - 16 Cloud and Moisture Channel Products
Overall Readiness Status – Green for DOE-4 and operational use time frames (Day 1)
Dissemination Methods
  Direct GOES-R Ground Segment to AWIPS Interface that are uplinked to the SBN for distribution to all sites
  Direct Read-Out for National Centers and select other sites, AR, PR (Expectation is that format will conform with GOES-R format on SBN)
AWIPS II Software Status
  AWIPS II Plugin complete, several tests with simulated data successfully executed
  Plugin available in AWIPS II 14.4.1 – Release Target June 2015
Risks and Mitigations
  Small risk that GOES-R actual data will differ from simulated data tested thus far
  Mitigation – Tests with Himawari data (same format as GOES-R) have been successful
NAWIPS Software Status
  NetCDF-4 capability in NAWIPS should allow access and display of GOES-R KPP Products, targeted to be implemented, August 2015
  Risks and Mitigations
    Risks - NAWIPS displays of GOES-R data not yet tested
    Mitigation - Plan to test with Himawari data and GOES-R simulated data

## Slide 5: Himawari Product Samples AWIPS II 14.4.1
Himawari Imagery Products Same Format as GOES-R Products

## Slide 6: NWS Satellite User Readiness GOES-R Derived Products
Product Summary - ~20 derived product types such as cloud top height, temperature and pressure to support forecast and warning processes for high-impact weather scenarios
Overall Readiness Status – Yellow for DOE-4, Green for Day 1 time frame of Sept. 2016
Dissemination Methods
  PDA to SBN using “standing subscription” interface for select products
  AWIPS II Data Delivery - Uses PDA Open Geospatial Consortium (OGC) for majority of products from the PDA
  Standing subscription to NCEP WAN for NCEP Centers
AWIPS II Software Status – Products available in 15.1.1 release – September 2015
  Aerosol Detection Aerosol Optical Depth Clear Sky Mask
  Cloud Optical Depth Cloud Particle Size Distb. Cloud Top Height
  Cloud Top Phase Cloud Top Pressure Cloud Top Temp
  Motion Winds Stability Indices Fire/Hot Spot
  Vert. Moisture Profile Vert. Temp. Profile Rainfall Rate/QPE
  Sea Surface Temp Snow Cover Volcanic Ash
  TPW
AWIPS II Software Status – Products targeted for 16.2.1 release – Spring 2016
  Lightning Detection Hurricane Intensity Estimate Fog and Low Cloud

## Slide 7: NWS Satellite User Readiness GOES-R Derived Products - Continued
Risks and Mitigations
  Data Delivery/PDA OGC Interface Risks
    Testing slower than planned due to network connectivity issues
    Emerging PDA security requirements will likely require more development making PDA Data Delivery with high likielihood not available for DOE 4 timeframe (Fall 2015)
  Data Delivery/PDA OGC Mitigations
    Use PDA Standing Subscription to SBN to support DOE 4
    Finalize security requirements to ensure that necessary development is completed before operational use date of derived products (September 2016)
  NAWIPS Readiness Risk
    NAWIPS NetCDF4 decoder not likely to handle all derived products
  NAWIPS Mitigations
    Centers use D2D perspective to support DOE 4
    Transition to NCP and/or develop NAWIPS capabilities to handle derived products in time for operational use date
    Tower-S mitigation being planned week of June 15

## Slide 8: NWS Satellite User Readiness S-NPP/JPSS Products
Product Summary - About 30 non-broadcast derived products such as active fires, aerosol/smoke suspended matter, and complete channel set for Visible Infrared Imaging Radiometer Suite (VIIRS) imagery, cloud, precipitation, ice and other products in support of ongoing forecast operations
Overall Readiness – S-NPP Near Constant Contrast Imagery
  Green for S-NPP VIIRS Near Constant Contrast (NCC) Imagery (Fall 2015)
  Yellow for Other Products - Incremental operational usage beginning 2016
Dissemination Methods
  SBN for NCC imagery all sites
  Data Delivery – PDA OGC interface for CONUS for other products
  Direct broadcast for Alaska Region (Expectation is that output will conform to SNPP/JPSS output standards, thus no unique AWIPS development required)
AWIPS II Software Readiness
  NCC imagery available in 15.1.1 September 2015
  Other products based on priority (Tower-S) targeted for 16.2.1, Spring 2016
Risk/Mitigations
  Data Delivery – Same as GOES-R derived products

## Slide 9: S-NNP/JPSS Product Sample in AWIPS II
S-NPP (VIIRS) of re-suspended ash analysis using Day Night Band. The operational implementation date for this capability is with 15.1.1 AWIPS release expected this fall.

## Slide 10: NWS Satellite User Readiness Other Mission Products
Product Summary: Global Precipitation Measurement (GPM), Sentinel Synthetic Aperture Radar (SAR), Soil Moisture Active Passive (SMAP), GCOM
Overall Readiness – Yellow
Dissemination Methods
  Data Delivery – PDA OGC interface for CONUS for most products
AWIPS II Software Readiness – Targeted Products for 16.2.1 Release (Spring 2016)
  GCOM AMSR-2 Microwave Imagery GCOM AMSR-2 Surface Wind Speed
  GPM GMI Microwave Imagery Sentinel and Radarsat-2 SAR Winds
  SMAP
Risk/Mitigations
  Data Delivery – Same as GOES-R derived products

## Slide 11: AWIPS Data Delivery and PDA
What is AWIPS II Data Delivery?
  Data Delivery uses “smart” push/pull technologies to allow AWIPS-II users to access data not routinely delivered via the Satellite Broadcast Network (SBN)
  Enables AWIPS to handle increased data volumes associated with major agency initiatives, e.g., GOES-R, Higher resolution models, etc.
  Key Features
    Data discovery of datasets residing on data provider systems, e.g., NOMADS, MADIS, Product Distribution and Access (PDA)
    Data access using subscriptions or ad hoc requests to support specific/unique forecaster requirements (e.g., fire weather or winter storm)
    Users can temporally, spatially, and/or parametrically subset datasets
      Reduces bandwidth demands
      Reduces data processing at receiving AWIPS sites
AWIPS Data Delivery and PDA Open Geospatial Consortium (OGC) Interface
  OGC interface supports data discovery, access and (on PDA system) subsetting
Candidate Satellite Product Categories for Data Delivery PDA Interface
  GOES-R – Derived Products
  SNPP/JPSS Derived Products, non-KPP imagery
  GPM, SMAP, NESDIS PDA Products not distributed via SBN, Sentinel, MeTOP imagery, OceanSAT

## Slide 12: Data Delivery High Level Architecture

## Slide 13: Data Delivery Status and Plans
Summer of 2015 Implementation (14.4.1)
  Access to MADIS
  Implementation of SBN subscription channel for shared subscriptions
  Roll out to select Regional HQs first, then select WFOs
PDA – AWIPS II Data Delivery Status
  Testing began March 2015
  Issues/Risks
    Network connectivity issues have slowed testing down
    Emerging new security requirements
    Data Delivery depends on limited AWIPS WAN bandwidth
  Mitigation
    Finalize security requirements, implement necessary development by Operational Day 1, Sept 2016.
    Experimental channel on SBN will be used for DOE-4
    AWIPS WAN upgrade project under IDP portfolio (See next brief)