## Slide 1
Day 1 Readiness
Discussion
Mike Johnson
June 16, 2015

## Slide 2: Definitions (Necessary for DAY 1 discussion)
1. Operational - versus - operational demonstration
  Operational = capability available via operationally configured systems (baseline dissemination & display)
    Organization commits to sustainment
    meets availability & latency requirements
  Operational Demonstration = proving ground demonstrations designed to simulate and evaluate possible future operational states

## Slide 3: Definitions (Necessary for DAY 1 discussion)
2. Day 1 User Readiness – degree to which AWIPS, Dissemination, Models, Trained Forecasters are ready when system is first operationally available.

## Slide 4: NWS Satellite User Readiness (Scope)
Multiple new satellite products expected next 18 months. Current "snapshot" of scope includes (~130 new products):
  Himawari (23 total / 12 critical)
  GOES-R Baseline (38 / 20)
  SNPP (38 / 25...most criticals for AR)
  GCOM ( 7 / 1)
  GOES-R added (11 / 2)
  GPM (11 / 4)
  Sentinel / Radarsat (1 / 1)
  SMAP (4 / 0)
  Direct Broadcast Unique (? / ?)
      CSPP-LEO (TBD)
      CSPP-GEO (TBD)

## Slide 5
LEGEND
Launch & Orbit Raising
Operations -
Post-launch Testing (PLT) - 180 Days
Outgas
System Performance Operational Test (SPOT)
12 Days
30 Days
60 Days
6 Mo
Post-Launch Assessment Review (PLAR) and Handover Readiness Review (HRR): Handover S/C Ops to OSPO
30 Days
PLPT
Ex-tended Val
<=5yrs Storage + >=8.4 Yrs Ops
Beta Stage Testing
Provisional Stage Testing
Validated Stage Testing
Peer-Stakeholder L1b & KPP Product Validation Review
Handover L1b & KPP Products to NWS
Peer-Stakeholder L2+ Product Validation Reviews
Handover L2+ Products to NWS
L+70Days
PLT End + 15Mo
ABI (L1b&CMI)
ABI (Other L2+)@
GLM (L2+)
SpWx (L1b)@
Products Not Yet Available to Public
Beta Validated Product
Provisionally Validated Product
Fully Validated Product
L+192Days
PLT Cal/INR
32 Days*
28 Days
L+87Days
L+ 86(MAG), 95(SUVI), 107(EXIS), 130(SEISS) Days
L+192Days
PLT End + 4Mo
L+103Days
L+139 Days
L+77Days
L+73Days
@ Maturity level may vary for each product, as product availability is driven by maturity of
algorithm implementation, as well as, the existence of science phenomena and associated ground-truth data.
9 Mo
PLT End + 12Mo
PLT End + 12Mo
PLT End + 12Mo
L+70Days
GOES-R Day 1
PLT/PLPT Activities (from Bob Iacovacci's Science Week Presentation)
* Data blackout due to Storage Mode Ops and Station Change to 105W.
Notes: Post-launch GOES-R cal/val activities. The top bar illustrates the GOES-R post-launch mission phases – Launch and Orbit Raising, Post-Launch Testing, and Operations. The Post-Launch Testing period includes a traditional observatory checkout, but also contains a period of Post-Launch Product Tests (PLPTs) designed for limited product quality assessment before Spacecraft Handover. After Handover, a period of Extended Validation is planned to enhance product science validation maturity. The colored lines in this figure represent the validation maturity stages of each product family – ABI L1b and Cloud and Moisture Imagery (CMI), ABI Other L2+, GLM L2+, and Space Weather L1b – and their association with post-launch mission phases. In this post-launch scenario, by Spacecraft Handover the expectation is that all L1b products and CMI will be Provisionally Validated, while all other products will be Beta Validated.

## Slide 6: Day 1 - GOES-R L2+ most of SNPP/JPSS Products (JPSS-GOES-R Schedule Conflict Upcoming Changes - Wanda Harding)
7/27 - 8/2
GRE Focus
12/4 – 12/18
GSIT 3
8/24 – 9/9
Impact. Val.
7/30 – 8/6
Impact. Val.
8/20 – 9/8
GSIT 2
DRAFT
12/20/15