## Slide 1: GOES-R Schedules for Data Release and Post-Launch Tests
Matt Seybold (OSPO/SPSD)
GOES-R Data Operations Manager
& PRO Team Lead
NOAA Satellite Proving Ground and User Readiness Meeting
May 9, 2016

## Slide 2: Agenda
Introduce the PRO Team
Review Data Release Strategy
Review Product Maturity Validation Levels
First Light Image Release

## Slide 3: PRO Team & CVCT (Cal/Val Coordination Team)
Dev I&T
Harris
CWG
Fred Wu (STAR)
AWG
Jaime Daniels (STAR)
GRB Simulators
Harris IT Services
Interfaces with External (Non-GOES-R) Assets
PRO Team Lead
OSPO “DOM” (Data Ops Manager)
Matt Seybold (OSPO)
Alg & Product Dev Lead
Randy Race
Product Quality Lead
(Cal/Val L1b)
Jon Fulbright
Product Ops Lead
(Cal/Val L2+)
Wayne MacKenzie (OSPO)
UPS Ops Lead
(GRB, HRIT/EMWIN) “PAL”
Acting – Kathryn Miretzky
User Services
Kathryn Miretzky
Cal/Val L2+ & L1 Support
Elizabeth McMichael
L1 Cal Tools
Dave Pogorzala
MST Liaison for
CM Support
Dawn Carter
GOES-R Assets
Non-GOES-R Assets
Vacant Positions
Dev Support
Jamese Sims (OSGS)
Quality Support
TBD NOAA Fed (GOES-R)
User Services Support
TBD NOAA Fed (OSPO)
UPS Ops
TBD NOAA Fed (OSPO)
NWS & Sat P.G.
NWS & NESDIS
PRO Deputy – Ops Transition Topics
OSPO “PAL” (Product Area Lead)
Wayne MacKenzie (OSPO)
Change Support
Ryan Williams
PRO Deputy – Program Topics
(Cal/Val & Admin)
Jon Fulbright
Development
Quality
Operations
Operations
Operations
CVCT consists of PRO, CWG, AWG, PSE (Program Sys Eng), OSPO Radiometric Engineers
Notes: Good to show a reminder of our org chart and note the hire of Jamese Sims.

## Slide 4: Data Release Strategy and Product Validation Reviews

## Slide 5: GOES-R Schedule Phases

## Slide 6: Data Release Strategy
  Ground Segment internal flow of instrument data: Commences upon completion of each instrument’s outgassing
  Data will flow for path integrity test purposes to PDA and AWIPS
  Data will flow for instrument vendor and CWG Cal/Val purposes to LZSS
  Data will not be released from LZSS, PDA, AWIPS to any other downstream consumers other than instrument vendors, CWG, and CLASS. The Unique Payload Services (GRB, HRIT/EMWIN, DCS) will also not yet distribute data.
  First media image(s) for ABI will be released after Orbit Raising and initial image navigation and radiometric assessment

## Slide 7: Data Release Strategy
External product distribution (PD): Commences upon completion of each instrument’s Post-Launch Tests (data will have Beta Maturity)
  Unique Payload Services [GRB, HRIT/EMWIN, DCS] will be populated
  LZSS, PDA, AWIPS will flow data to their respective, integrated, downstream consumers
  Estimated dates for completion of each instrument’s Post-Launch Tests:
    ABI @ L+88, EXIS @ L+92, MAG @ L+93, SUVI @ L+104, SEISS @ L+139, GLM @ L+148
Internal Flow

## Slide 8: Data Release Strategy
Operations Handover from GOES-R to OSPO: L+6 Months
Internal Flow
External Distribution

## Slide 9: Data Release Strategy
GOES-R Assignment to East or West Position: L+12 Months
Internal Flow
External Distribution
Operations
Handover

## Slide 10: Recap: Data Release Strategy
Internal Flow
L+15 Days
External Distribution
L+88 Days
Operations Handover
L+6 Months
East/West Assignment
L+12 Months
Instrument | Distribution Commences
ABI | L+88
EXIS | L+92
MAG | L+93
SUVI | L+104
SEISS | L+139
GLM | L+148

## Slide 11: Detailed Data Release Strategy
Declaration of Maturity
Milestones occurs at
Peer-Stakeholder Product
Validation Reviews (PS-PVRs)
Internal Flow
L+15 Days
External Distribution
L+88 Days
Handover Readiness
Review (HRR) &
Operations Handover
L+6 Months
East/West Assignment
L+12 Months

## Slide 12: Product Maturity Levels
What do the Product Maturity Levels mean? There is a PS-PVR at each stage as a method of informing the user community of the following readiness for use:
Beta: Products are made available to users to gain familiarity with data formats and parameters. It has been minimally validated and may still contain significant errors and is not optimized for operational use.
Provisional: Product ready for operational use but has documented known issues. Product analyses are sufficient to communicate product performance to users relative to expectations.
Full: Product is operational. All known product anomalies are resolved and/or documented and shared with the user community.

## Slide 13: What is a PS-PVR?
A Peer Stakeholder - Product Validation Review (PS-PVR) appraises the status of product quality with respect to Program definitions. The PS-PVR Panel has the authority to declare products have achieved a product maturity level and provides guidance on work expected to achieve the next maturity level.
Instrument
Vendor
Analysis (L1b)
CWG / AWG
Analysis
Declaration
Of
Product Maturity Level
Customer
Forums
(ABI L2+, including CMI, GLM L2+)
PS-PVR
Chair: Steve Goodman, GOES-R Program Scientist
Panel (consolidated recommendations to Chair): NOAA GOES Operational Requirements Working Group and GOES-R PSE
Presenters: CWG and AWG
Users: NOAA Line Offices (NWS, NOS, NMFS, OAR, OMAO)

## Slide 14: Focus during PS-PVRs
What will be the focus of the PS-PVR at the different maturity levels?
Beta:
Review present state of PLT activities and results
Consider initial product quick looks
Affirm release of data products to public
Provisional:
Review present state of PLPT activities and results
Compare initial assessment to predicted performance
Discuss user feedback, known anomalies, and remediation strategies
Recommend path to predicted performance
Full:
Review present state of continuing cal/val activities and results
Compare ongoing assessment to predicted performance
Recommend further optimization activities, considering mission parameters and priorities
Affirm dissemination of product quality assessment to public

## Slide 15: Tentative PS-PVR Schedule Given 10/13 Launch

## Slide 16: PLPT Science Validation Success Criteria: Determination
GOES-R LIRD, MRD, PORD Requirements
Instrument Design, Fabrication, and Test
Instrument Performance
Model Analysis to Predict On-Orbit Product Performance
GOES-R CONOPS
Defined PLPT Analysis Methods and Val Reference Data Spatial/Temporal Coverage Limits (in RIMPs)
PLPT Analysis to Determine On-Orbit Product Performance
Comparison between determined and predicted on-orbit product science performance
GOES-R Post-Launch Validation:
The process of determining that the deliverable item satisfies its intended use in its intended environment. A post-launch re-certification of pre-launch predicted performance.
GOES-R Pre-Launch Verification:
The process of determining that the deliverable item meets specified requirements, using methods such as test, demonstration, analysis, and inspection.
BASELINE

## Slide 17: First Public Image Release

## Slide 18: First Public Image Release
The first public image of ABI will be notionally released 61 days after launch.
  The following tentative criteria must be met before image release:
    Full disk image navigation and radiometric accuracy is qualitatively acceptable (e.g., no inversion, minimal striping, no clear saturation)
    Visibly free of non-physical artifacts
    Image is captured during local daylight hours with significant discernible geographic features (e.g. moderate cloud cover)
    All 16 channels meet above criteria
    No open flight (spacecraft or instrument) or ground incident reports preventing instrument readiness for first image broadcast
    Vendor and science teams GO
    Program and project management GO
  Data mock-ups are in hand and now turning to Outreach Coordinators for story-board layouts and PLT release plan

## Slide 19: Questions?